## Sheet1
Task | Priority level | Responsible person | Month | State
meeting 1 - Initial Product Concept | #1 | Tianyi Wang | Month 1 | Completed | Capstone Lite (Meetings 1-~15, ~3 Months ):
Complete research on tech stack | #2 | Tianyi Wang | September | Completed
Project concepts 1 page | #2 | Tianyi Wang | September | Completed
Complete the timeline | #2 | Tianyi Wang | September | Completed
meeting 2 - Initial Product Concept | #1 |  | Month 1 | In progress
meeting 3 - Initial Product Concept | #1 |  | Month 1 | In progress | Checkpoint 1 (End Mtg 3): Initial Product Concept.
meeting 4 - Design & Technical Planning | #1 |  | Month 1 | In progress |  | Deliverables: Project timeline, Product concept one-pager.
meeting 5 - Design & Technical Planning | #1 |  | Month 2 | Not started
meeting 6 - Design & Technical Planning | #1 |  | Month 2 | Not started | Checkpoint 2 (End Mtg 6): Design & Technical Planning.
meeting 7 - Development Environment & Basic Structure | #1 |  | Month 2 | Not started |  | Deliverables: Screenshots of wireframes/mockups.
meeting 8 - Development Environment & Basic Structure | #1 |  | Month 2 | Not started
meeting 9 - Development Environment & Basic Structure | #1 |  | Month 3 | Not started | Checkpoint 3 (End Mtg 9): Development Environment & Basic Structure.
meeting 10 - Core Functionality Implementation | #1 |  | Month 3 | Not started |  | Deliverables: Link to GitHub Repository with initial code structure.
meeting 11 - Core Functionality Implementation | #1 |  | Month 3 | Not started | Checkpoint 4 (End Mtg 11): Core Functionality Implementation.
meeting 12 - Core Functionality Implementation | #1 |  | Month 3 | Not started |  | Deliverables: Screen recording of core functionality implementation.
meeting 13 - Core Functionality Implementation | #1 |  | Month 4 | Not started | Checkpoint 5 (End Mtg 13): MVP Developed.
meeting 14 - Basic User Interface & Initial Testing | #1 |  | Month 4 | Not started |  | Deliverables: Screen recording of functional MVP.
meeting 15 - Basic User Interface & Initial Testing | #1 |  | Month 4 | Not started | Checkpoint 6 (End Mtg 15): Basic User Interface & Initial Testing (5+ users).
meeting 16 - Basic User Interface & Initial Testing | #1 |  | Month 4 | Not started |  | Deliverables: Screenshots of basic UI design, Screenshot/documentation of names & feedback of 5+ users.
Market Scan/Research of CS education products | #1 | Tianyi Wang | Month 1 | In progress
Listing important features and how they can be met | #1 | Tianyi Wang | Month 1 | In progress
Learning HTML | #1 | Tianyi Wang | Month 1 | Close to Completion
Learning CSS | #1 | Tianyi Wang | Month 1 | In progress
Creating a testing barebones website | #1 | Tianyi Wang | Month 2 | Not started
Designing looks for the website | #1 | Tianyi Wang | Month 2 | Complete
purchasing a domain for the website | #1 | Tianyi Wang | Month 3 | Not started
Identifying issues and bugs and fixing them | #1 | Tianyi Wang | Month 3 | Not started
Learning and understanding Backends and Databases | #1 | Tianyi Wang | Month 4 | Not started
Collect information and resources of CS courses | #1 | Tianyi Wang | Month 4 | Not started
Get students or users to beta test the product | #1 | Tianyi Wang | Month 5 | Not started
Polish the product in terms of info and aesthetics | #1 | Tianyi Wang | Month 6 | Not started
Completing the website | #1 | Tianyi Wang | Month 6 | Not started
Launching the website | #1 | Tianyi Wang | Month 6 | Not started